## Sheet1
| Hugo Baird | Cedric Stephani | Leon Hoogenraad | Vainui Moresi | Husam Alghamdi
Week 1 | Idea selection, planning and overview of functionality, target audience and use case. | Idea selection, planning and overview of functionality, target audience and use case. | Idea selection, planning and overview of functionality, target audience and use case. | Idea selection, planning and overview of functionality, target audience and use case. | Idea selection, planning and overview of functionality, target audience and use case.
Week 2 | Feasibility study | Feasibility study | User stories | Feasibility study | Feasibility study
Week 3 | Gave instructions on how to download Microsoft Visual Code, ReactJS, Node.JS and MongoDB. Create starting React project base structure and push to Git. Ensure all group members can pull the project and run the react App in their browser. Assist with scheduling and delegating of stories. | Downloaded the systems programs like Visual Code, ReactJS/NodeJS, and MongoDB. Worked on user stories and project scheduling as well as started working on a rough database model which reflects systems/user stories needs. | Downloaded and Installed development tools onto both my desktop and laptop. Participated in the planning poker session to estimate time cost of each user story. | Downloaded our chosen software for the project: ReactJS, NodeJS, MongoDB and Visual Studio Code. Have watched a few tutorials to start learning these softwares. | Downloaded softwares to work in project in accordance with team plan, which are: ReactJS,NodeJS, MongoDB and Visual Studio Code. Contributed to User-Stories and Created project page on taiga. Added Activity digram for Agora and contribute to playing planning poker with the rest of the team.
Week 4 | Created Hi-FI prototypes for Home and View Listing screens. Found suitable tutorial videos for the group to watch to learn React and assist with project development. Start development of the Home screen and set up appropriate project directory structure. | Updated the ERD, Created a MongoDB cluster/database which everyone has been added to, alongside found tutorials for how to get it working on various OS's. Worked on the evidence review. And have also made low-fi and hi-fi prototypes for the computer and mobile webpages, and a sequence diagram. | Created Hi-Fi Mockups for Create a Listing and View Profile pages. Also wrote up requirements gathering and estimation & schedule sections on the evidence review. Also pracitced further with NodeJS and React JavaScript libraries. | Created lo-fi and hi-fi prototypes for various pages (Login, Home, Register, List Product, Buy product). Carrying on with tutorial watching for the new development tools. Have started on a heuristics document for user experience in the context of our project. | Create mockup prototype for Purchase confirmation, checkout, credit card, About us and contact us. Created login sequence diagram, use case diagram and updated activity diagram.
Week 5 | Proposed chosen architecture pattern to team members (layered). Documented in-depth architecture section of the evidence review. Designed visual architecture model with relative components. Started focus on implementation of home screen and displaying listings. Helped other team members learning and understanding of React and set up the groundwork of the project (screen renders in App.js) to start development. | Created a form for the create account page which has since been put into a text file for now as we work on simplifying it until we know it works correctly. Also have set up the majority of the back end database as well as the middleware to connect these two. Just working out the final bugs with Leon before connecting it all together. | Set up the node js server file to pull data from the backend and serve it to the frontend. Set up a communal email and MongoDB account for the team to use. Provided instructions for team to install npm backend modules (these are in instructions.txt in the gitbucket repo). Working with Cedric to pull data from the sign up form to the backend. | Started front-end work regarding the main page through following tutorials suggested by the team. Helped explain the models within the feasibility study and did some proof reading/editing. Finished the heuristics document for user experience. Getting used to the new tools, so far so good. | Worked on the Evidence review, watched tutorials to learn about react.js, Node js and MongoDB. Downloded dependency for as instructions to VSC and started styling front-end pages
Week 6 | Successfully fetched the listing data from the server and mongoDB. Completed styling of listings and the home page (header navigation bar, containers). Helped other team members with issues related to sign up/sign in and server operations. Started planning implementation of the create listing form. Created a Heroku account using the Agora email for future deployment. | Helped implement the back end side of the sign in and sign up pages as well as did some more editing to the front side of the features too. Ran into some issues so it took longer than me and Leon had initially thought it would. |  | Received help from Al on direction for styling and page creations (to make profile page and create listing page). Finally troubleshooted annoying local issues and now am working fine. Started on profile page styling within react.js app. | designed a logo for the student marketplace with couple of color combos and had the team to vote for one. Styled some of frontend pages (about us, sign in, contact us) and tested them locally to ensure they are proply working before integrate them to react.js app.
Week 7 |  |  |  | Started work on a responsive nav-bar. Ran into issues again so have repulled repo and created a separate branch for the navbar. Adding css styling to navbar elements and have begun to implement functionality for when a user clicks on the menu.
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13