## Sheet1
| Hugo Baird | Cedric Stephani | Leon Hoogenraad | Vainui Moresi | Husam Alghamdi
Week 1 | Idea selection, planning and overview of functionality, target audience and use case. | Idea selection, planning and overview of functionality, target audience and use case. | Idea selection, planning and overview of functionality, target audience and use case. | Idea selection, planning and overview of functionality, target audience and use case. | Idea selection, planning and overview of functionality, target audience and use case.
Week 2 | Feasibility study | Feasibility study | User stories | Feasibility study | Feasibility study
Week 3 | Gave instructions on how to download Microsoft Visual Code, ReactJS, Node.JS and MongoDB. Create starting React project base structure and push to Git. Ensure all group members can pull the project and run the react App in their browser. Assist with scheduling and delegating of stories. | Downloaded the systems programs like Visual Code, ReactJS/NodeJS, and MongoDB. Worked on user stories and project scheduling as well as started working on a rough database model which reflects systems/user stories needs. | Downloaded and Installed development tools onto both my desktop and laptop. Participated in the planning poker session to estimate time cost of each user story. | Downloaded our chosen software for the project: ReactJS, NodeJS, MongoDB and Visual Studio Code. Have watched a few tutorials to start learning these softwares. | Downloaded softwares to work in project in accordance with team plan, which are: ReactJS,NodeJS, MongoDB and Visual Studio Code. Contributed to User-Stories and Created project page on taiga. Added Activity digram for Agora and contribute to playing planning poker with the rest of the team.
Week 4 | Created Hi-FI prototypes for Home and View Listing screens. Found suitable tutorial videos for the group to watch to learn React and assist with project development. Start development of the Home screen and set up appropriate project directory structure. | Updated the ERD, Created a MongoDB cluster/database which everyone has been added to, alongside found tutorials for how to get it working on various OS's. Worked on the evidence review. And have also made low-fi and hi-fi prototypes for the computer and mobile webpages, and a sequence diagram. |  | Created lo-fi and hi-fi prototypes for various pages (Login, Home, Register, List Product, Buy product). Carrying on with tutorial watching for the new development tools. Have started on a heuristics document for user experience in the context of our project. | Create mockup prototype for Purchase confirmation, checkout, credit card, About us and contact us. Created login sequence diagram, use case diagram and updated activity diagram.
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13